## Test_Execution
ElderCare Connect - Manual Test Cases
Test Case ID | Module | Test Scenario | Execution Date | Tester | Environment | Status | Actual Result | Bug ID | Remarks
LOG-001 | Login | Valid Staff login | 2026-02-11 | Aziz Subhani | Local | Passed | Staff logged in successfully and Staff Dashboard was displayed. | —
LOG-002 | Login | Valid Guardian login | 2026-02-11 | Aziz Subhani | Local | Passed | Guardian logged in successfully and Guardian Dashboard was displayed. | —
LOG-003 | Login | Valid Admin login | 2026-02-11 | Aziz Subhani | Local | Passed | Admin logged in successfully and Admin Dashboard was displayed. | —
LOG-004 | Login | Invalid password | 2026-02-11 | Aziz Subhani | Local | Passed | Login was rejected when an incorrect password was entered. | —
LOG-006 | Login | Empty email validation | 2026-02-11 | Aziz Subhani | Local | Passed | Validation was displayed for the required email field. | —
UM-001 | User Management | Create Staff account | 2026-02-23 | Aziz Subhani | Local | Passed | Staff account was created successfully with valid information. | —
UM-002 | User Management | Create Guardian account | 2026-02-23 | Aziz Subhani | Local | Passed | Guardian account was created successfully with valid information. | —
UM-003 | User Management | Create Resident account | 2026-02-23 | Aziz Subhani | Local | Passed | Resident account was created successfully with valid information. | BUG-006 if applicable
ADM-001 | Admin | Admin Dashboard access | 2026-02-23 | Aziz Subhani | Local | Passed | Admin Dashboard loaded successfully after valid admin login. | —
ADM-008 | Admin | Assign Resident to Staff | 2026-02-23 | Aziz Subhani | Local | Passed | Admin successfully assigned staff to the residents. | BUG-007 if applicable
STF-001 | Staff | Staff Dashboard access | 2026-02-23 | Aziz Subhani | Local | Passed | Staff Dashboard loaded successfully. | —
STF-002 | Staff | View assigned Residents | 2026-02-23 | Aziz Subhani | Local | Passed | Assigned Resident information was displayed correctly. | —
STF-010 | Staff | Submit daily report | 2026-02-23 | Aziz Subhani | Local | Passed | Daily report was submitted successfully with valid information. | —
STF-012 | Staff | Edit submitted report | 2026-02-23 | Aziz Subhani | Local | Passed | Previously submitted report was edited successfully. | —
GRD-001 | Guardian | Guardian Dashboard access | 2026-02-23 | Aziz Subhani | Local | Passed | Guardian Dashboard loaded successfully. | —
GRD-003 | Guardian | View latest Resident report | 2026-02-23 | Aziz Subhani | Local | Passed | Latest Resident report was displayed correctly. | —
GRD-013 | Guardian | Prevent report modification | 2026-02-23 | Aziz Subhani | Local | Passed | Guardian was prevented from editing Resident reports. | —
RES-001 | Resident | Resident Dashboard access | 2026-02-23 | Aziz Subhani | Local | Passed | Resident Dashboard loaded successfully. | —
RES-003 | Resident | Start audio recording | 2026-03-02 | Aziz Subhani | Local | Passed | Audio recording started successfully. | —
RES-004 | Resident | Stop audio recording | 2026-03-02 | Aziz Subhani | Local | Passed | Audio recording stopped successfully. | —
AUD-005 | Audio Recording | Submit recorded audio | 2026-03-02 | Aziz Subhani | Local | Passed | Resident can stored audio message successfully into the database. | BUG-002 / BUG-003 if applicable
REP-013 | Reports | Verify report date | 2026-03-02 | Aziz Subhani | Local | Passed | Verify the report data with the particular resident's voice sentiment analysis. | BUG-001 if applicable
SEN-001 | Sentiment Analysis | Start sentiment analysis | 2026-04-04 | Aziz Subhani | Local | Passed | Sentiment works properly just after submitted the report. | BUG-004 if applicable
SEN-003 | Sentiment Analysis | Negative sentiment detection | 2026-04-04 | Aziz Subhani | Local | Passed | Negative sentiment was correctly identified for the tested negative input. | —
SEN-005 | Sentiment Analysis | Guardian views sentiment | 2026-04-04 | Aziz Subhani | Local | Passed | Guardian was able to view the generated sentiment result. | —
LOG-012 | Security | Prevent unauthorized dashboard access | 2026-04-26 | Aziz Subhani | Local | Passed | Unauthorized access to the restricted dashboard was prevented. | —
LOG-015 | Security | Prevent unauthorized resource access | 2026-04-26 | Aziz Subhani | Local | Passed | Unauthorized resource access was prevented. | —
GRD-014 | Security | Prevent Guardian access to another Resident | 2026-04-26 | Aziz Subhani | Local | Passed | Guardian was prevented from accessing another Resident's data. | —
STF-015 | Staff | Staff logout | 2026-02-23 | Aziz Subhani | Local | Passed | Staff logged out successfully and was redirected appropriately. | —
GRD-015 | Guardian | Guardian logout | 2026-02-23 | Aziz Subhani | Local | Passed | Guardian logged out successfully. | —
RES-015 | Resident | Resident logout | 2026-02-23 | Aziz Subhani | Local | Passed | Resident logged out successfully. | —